TransIQ

Jamaica's AI-Powered Public Transport Intelligence App

─────────────────────────────────

Project Scope & Game Plan

Intellibus Hackathon 2026  |  March 14–15, 2026

National Arena, Kingston, Jamaica

| Team Jodel · Ayanna · Abby · Brit · Richard | Prize Pool $15,000+ USD · 1st Place $5,000 |
| --- | --- |

# 1. Executive Summary

What is TransIQ? TransIQ is Jamaica's first AI-powered public transport intelligence mobile app. It enables commuters, students, workers, and independent travelers to navigate Jamaica's fragmented public transport network — covering Route Taxis, JUTC Buses, Knutsford Express, JUTA, and Uber — by providing three optimized travel plans (Fastest, Cheapest, Balanced) powered by live web-scraped data and machine learning models.

TransIQ directly addresses the absence of any unified digital transport solution in Jamaica, a market gap that affects millions of daily commuters island wide. Built for the Intellibus Hackathon 2026, TransIQ is architected for real-world deployment and long-term scalability.

| Category | Detail |
| --- | --- |
| App Name | TransIQ |
| Platform | React Native — iOS & Android |
| Hackathon | Intellibus Hackathon 2026 |
| Event Date | March 14–15, 2026 |
| Venue | National Arena, Kingston, Jamaica |
| Target Market | Jamaican commuters, students, workers, independent travelers |
| Secondary Market | Tourism — independent travelers exploring Jamaica |

# 2. Project Scope

## 2.1  In Scope

The following are confirmed deliverables for the hackathon submission:

### Mobile App (React Native — iOS & Android)

- Login and Sign Up screens with JWT authentication

- Home screen with Uber-style 'Where to?' search, budget filter, and time preference

- Route Results screen displaying three ML-powered plans — Fastest, Cheapest, Balanced

- Travel Plan Detail screen with step-by-step journey breakdown

- Interactive Live Map screen using Google Maps SDK with colour-coded route segments

- Account screen with saved routes, trip history, and safety preferences

- Push notifications for traffic alerts and safety check-ins

### Transport Coverage

- Route Taxis — all major Kingston and island wide routes

- JUTC Buses — full schedule and fare data

- Knutsford Express — inter-parish routes

- JUTA — tourism-focused routes

- Uber — live fare estimates via Uber API

### Machine Learning Models

- Model 1 — ETA Prediction: predicts actual trip duration in minutes

- Model 2 — Fare Prediction: predicts actual trip cost in JMD

- Model 3 — Traffic Congestion Level: predicts route congestion

- Model 4 — Best Departure Time: recommends optimal leave time

- Model 5 — Route Reliability Score: rates route consistency

- Model 6 — Safety Score: rates route safety by time of day

### Data Pipeline

- Web scraper for ta.org.jm/available-routes — licensed taxi routes

- Web scraper for ta.org.jm/routes-and-fares — official fare prices

- JUTC website scraper — bus schedules and stops

- Google Maps API — live real-time traffic conditions

- Jamaica Meteorological Service — weather and flood alerts

- Uber API — real-time fare estimates and surge pricing

- Auto-refresh pipeline every 15 minutes via scheduled jobs

### Safety Features (Richard)

- Emergency SOS button — one tap sends GPS location to emergency contact

- Off-route detection — GPS monitors deviation from planned route

- Check-in prompt — notifies user when they should have arrived

- Safety score per route — displayed on route results screen

### Backend & Infrastructure

- Java Spring Boot REST API

- Apache Kafka — real-time traffic event streaming to mobile app

- PostgreSQL — live route, user, and trip data

- Snowflake — analytics data warehouse (commuter trends, impact metrics)

- AWS EKS, Lambda, API Gateway — cloud deployment

- Terraform — infrastructure as code

- GitHub Actions + AWS CodePipeline — CI/CD automated deployment

## 2.2  Out of Scope

The following will NOT be built for the hackathon submission:

- In-app payment or ticket purchasing

- Driver or operator-facing dashboard (post-hackathon roadmap)

- Live vehicle GPS tracking (requires hardware integration)

- Offline mode

- Languages other than English

## 2.3  Assumptions

- Synthetic dataset will be used as fallback if live scrapers fail during the event

- Google Maps SDK will be used for navigation — no custom mapping engine

- ML models will be pre-trained before hackathon day and deployed on arrival

- All team members will have their pre-build tasks completed before March 14

# 3. Team Roles & Responsibilities

| Team Member | Role | Core Responsibilities |
| --- | --- | --- |
| Jodel | Web Scraping & Data Pipeline | Build scrapers for ta.org.jm, JUTC, traffic, and weather. Load and maintain the live database. Schedule auto-refresh jobs. |
| Ayanna | ML Engineer | Train all 6 ML models in Google Colab. Export models as .pkl files. Deploy to AWS Lambda. Monitor model accuracy. |
| Abby | Mobile Frontend Developer | Build React Native screens: Login, Home, Route Results. Connect to backend API. Implement Google Maps SDK. |
| Brit | Mobile Frontend Developer | Build React Native screens: Travel Detail, Account, Services. Handle UI state management. Ensure mobile responsiveness. |
| Richard | Safety Features & Backend | Build SOS button, off-route GPS detection, check-in alerts. Support Spring Boot API endpoint development. |

# 4. Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Mobile App | React Native (TypeScript) | iOS and Android app from a single codebase |
| Maps | Google Maps SDK for React Native | Live navigation and route visualisation |
| Backend | Java Spring Boot | REST API, routing logic, user authentication |
| Real-Time | Apache Kafka | Live traffic event streaming to the mobile app |
| Database | PostgreSQL | User data, routes, live trip records |
| Analytics | Snowflake | Historical data warehouse, impact metrics |
| ML Models | Python (scikit-learn) → AWS Lambda | ETA, fare, traffic, and safety predictions |
| Cloud | AWS (EKS, Lambda, API Gateway) | Cloud-native deployment |
| Infrastructure | Terraform | Infrastructure as code provisioning |
| CI/CD | GitHub Actions + AWS CodePipeline | Automated build and deployment pipeline |
| Scrapers | Python (BeautifulSoup / Selenium) | Live data collection from transport sources |

# 5. Game Plan — Phase Breakdown

Core Strategy Build everything that can be built BEFORE hackathon day. On the day, the team is assembling and connecting pre-built pieces — not building from scratch under 24-hour pressure. Every person should arrive with their component working independently.

## Phase 1 — Pre-Hackathon Preparation (Now → March 13)

Everything in this phase must be completed before arriving at the venue. This is the most important phase.

### Jodel — Data Pipeline

- Write and test scraper for ta.org.jm/available-routes

- Write and test scraper for ta.org.jm/routes-and-fares

- Write scraper for JUTC schedule page

- Set up Google Maps API key for live traffic

- Create and populate PostgreSQL schema with scraped data

- Test auto-refresh scheduler — confirm data updates every 15 minutes

- Verify fallback to synthetic dataset if scraper fails

### Ayanna — ML Models

- Run full notebook in Google Colab — train all 6 models

- Validate model accuracy: ETA MAE under 8 minutes, Fare MAE under JMD 50

- Export all .pkl files: eta_model, fare_model, traffic_model, departure_model, reliability_model, safety_model

- Write Python Flask wrapper to serve predictions as REST API

- Package as AWS Lambda function — ready to deploy on the day

- Test Lambda function locally with sample inputs

### Abby & Brit — Mobile Frontend

- Initialise React Native project with TypeScript

- Install and configure Google Maps SDK

- Set up React Navigation — screen routing working

- Build Login and Sign Up screens

- Build Home screen with search bar and filters

- Build Route Results screen with 3 plan cards

- Build placeholder screens for Map, Account, Services

- Connect frontend to backend API base URL

### Richard — Safety & Backend

- Research React Native Location and Notification APIs

- Build SOS button component — sends GPS coordinates to emergency contact

- Build off-route detection logic using GPS coordinates

- Build check-in notification scheduler

- Set up Spring Boot project structure and base API endpoints

- Test safety features on a physical device

### All Team Members

- Create GitHub repository 'transiq' — set to private

- All team members added as collaborators

- Create Notion workspace — pages: Roadmap, Roles, Notes, Pitch

- Create shared Google Drive folder — upload dataset and Colab notebook

- Set up WhatsApp or Discord group for daily communication

- Each member pushes their pre-built code to GitHub before March 13

## Phase 2 — Hackathon Day 1 (March 14)

Priority Rule Build in this exact order. Do not move to the next item until the current one is working. A fully working core beats an incomplete full feature set every time.

| Time | Task | Who | Done When |
| --- | --- | --- | --- |
| Hour 0–1 | Team arrives, set up laptops, deploy AWS infrastructure with Terraform, confirm GitHub Actions pipeline is live | All | Live URL accessible from phone |
| Hour 1–3 | Deploy ML Lambda functions, confirm predictions returning correctly via API | Ayanna | curl to Lambda returns ETA + fare JSON |
| Hour 1–3 | Deploy scrapers, confirm live data in PostgreSQL, Kafka topics created | Jodel | DB has fresh route and fare data |
| Hour 1–4 | Connect Home screen search → Spring Boot API → ML predictions → Results screen | Abby + Richard | Full trip search returning 3 plans |
| Hour 4–6 | Kafka traffic event fires → ETA updates on mobile app in real time | Richard + Jodel | Demo: trigger event, watch ETA change |
| Hour 6–9 | Google Maps live navigation screen — route segments colour-coded | Brit + Abby | Map shows route from A to B |
| Hour 9–12 | User auth — login, register, save routes, trip history | Abby + Richard | Login flow working end to end |

## Phase 3 — Hackathon Day 2 (March 15)

| Time | Task | Who | Done When |
| --- | --- | --- | --- |
| Hour 12–15 | Safety features — SOS button live, off-route detection working | Richard | SOS sends location, off-route triggers alert |
| Hour 12–15 | Snowflake analytics — route trends, commuter stats, impact counter | Jodel + Ayanna | Dashboard shows live impact numbers |
| Hour 15–18 | Account screen, saved routes, notification preferences | Brit | User can save and reload routes |
| Hour 18–20 | Polish UI — fix any visual bugs, ensure smooth transitions | Abby + Brit | App looks clean on both iOS and Android |
| Hour 20–22 | Pre-load demo data — 5 users, realistic trip histories, saved routes | All | App never looks empty during demo |
| Hour 22–24 | Rehearse 5-minute demo script 3 times. Write README. Submit to GitHub. | All | Submission confirmed on Devpost |

## Phase 4 — Demo Day Presentation

The 5-minute demo must follow this exact script to maximise judge impact:

- Minute 0:30 — Open with the problem: 'Every day millions of Jamaicans have no idea how to get from A to B affordably. There is no app for this.'

- Minute 1:00 — Show TransIQ: 'This is TransIQ — Jamaica's first AI transport intelligence app.'

- Minute 1:30 — Live demo: enter Spanish Town → Downtown Kingston, 7:30am Monday, JMD 500 budget. Show the 3 plans appear.

- Minute 2:30 — Trigger a live Kafka traffic event on Washington Blvd. Show the ETA update in real time on screen. This is the wow moment.

- Minute 3:00 — Show the map with colour-coded route segments and the SOS button.

- Minute 3:30 — Show the Snowflake impact dashboard: routes planned, avg time saved, avg money saved.

- Minute 4:00 — Business case: 'This is a $4 billion tourism market. We've already spoken to Ministry of Transport. This scales across every Caribbean island.'

- Minute 4:30 — SPAIN checklist: Stability, Performance, Availability, Integrity, Novelty — walk judges through each.

- Minute 5:00 — Close: 'TransIQ is live, deployed, and ready. Jamaica's transport network finally has its backbone.'

# 6. Action Items

Every action item must be completed before arriving at the hackathon venue. Items marked Critical will block other team members if not done on time.

## 6.1  Jodel — Web Scraping & Data

| # | Action Item | Owner | Timeline | Priority |
| --- | --- | --- | --- | --- |
| J1 | Scrape ta.org.jm/available-routes — extract all route names, start/end hubs, route IDs | Jodel | Before March 10 | Critical |
| J2 | Scrape ta.org.jm/routes-and-fares — extract base fares per route | Jodel | Before March 10 | Critical |
| J3 | Scrape JUTC website — extract bus routes, schedules, stop locations, fares | Jodel | Before March 11 | Critical |
| J4 | Set up Google Maps API key and test live traffic data return | Jodel | Before March 11 | High |
| J5 | Set up PostgreSQL schema — tables: routes, hubs, trips, traffic_events, ml_predictions | Jodel | Before March 12 | Critical |
| J6 | Load all scraped data into PostgreSQL and verify row counts | Jodel | Before March 12 | Critical |
| J7 | Write 15-minute auto-refresh scheduler for routes and fare data | Jodel | Before March 13 | High |
| J8 | Set up Kafka topics: traffic-events, route-updates, trip-status | Jodel | Before March 13 | High |
| J9 | Test fallback to synthetic dataset if any scraper fails | Jodel | Before March 13 | Medium |

## 6.2  Ayanna — ML Models

| # | Action Item | Owner | Timeline | Priority |
| --- | --- | --- | --- | --- |
| A1 | Run full Google Colab notebook — train all 6 models on the synthetic dataset | Ayanna | Before March 10 | Critical |
| A2 | Validate ETA model accuracy — MAE must be under 8 minutes | Ayanna | Before March 10 | Critical |
| A3 | Validate fare model accuracy — MAE must be under JMD 50 | Ayanna | Before March 10 | Critical |
| A4 | Export all 6 model .pkl files and encoder files | Ayanna | Before March 10 | Critical |
| A5 | Write Python Flask wrapper — serves all 6 models as REST endpoints | Ayanna | Before March 11 | Critical |
| A6 | Package Flask app as AWS Lambda function — zip file ready to deploy | Ayanna | Before March 12 | Critical |
| A7 | Test Lambda function locally — confirm JSON input/output format with team | Ayanna | Before March 12 | High |
| A8 | Document model input features and output format for backend team | Ayanna | Before March 12 | High |
| A9 | Retrain models on live scraped data once Jodel's DB is ready | Ayanna | Before March 13 | Medium |

## 6.3  Abby & Brit — Mobile Frontend

| # | Action Item | Owner | Timeline | Priority |
| --- | --- | --- | --- | --- |
| F1 | Initialise React Native project with TypeScript — push to GitHub | Abby | Before March 10 | Critical |
| F2 | Install and configure Google Maps SDK for React Native | Abby | Before March 10 | Critical |
| F3 | Set up React Navigation — all screen routes configured | Brit | Before March 10 | Critical |
| F4 | Build Login and Sign Up screens — matching approved design | Brit | Before March 11 | Critical |
| F5 | Build Home screen — search bar, budget slider, time filter, recent trips | Abby | Before March 11 | Critical |
| F6 | Build Route Results screen — 3 plan cards with all data fields | Abby | Before March 12 | Critical |
| F7 | Build Travel Plan Detail screen — step-by-step journey view | Brit | Before March 12 | High |
| F8 | Build Account screen — saved routes, stats, safety toggles | Brit | Before March 12 | High |
| F9 | Build Live Map screen — Google Maps with colour-coded route segments | Abby | Before March 13 | High |
| F10 | Connect frontend to backend API base URL — test with mock responses | Abby + Brit | Before March 13 | Critical |
| F11 | Test full app on both iOS and Android physical devices | Abby + Brit | Before March 13 | High |

## 6.4  Richard — Safety & Backend

| # | Action Item | Owner | Timeline | Priority |
| --- | --- | --- | --- | --- |
| R1 | Research React Native Location API and Notification API — document usage | Richard | Before March 10 | High |
| R2 | Build SOS button component — one tap sends GPS coordinates to emergency contact | Richard | Before March 11 | Critical |
| R3 | Build off-route detection — GPS compares current position to planned route | Richard | Before March 12 | Critical |
| R4 | Build check-in notification — alerts user when expected arrival time is reached | Richard | Before March 12 | High |
| R5 | Set up Spring Boot project — base structure, config files, push to GitHub | Richard | Before March 10 | Critical |
| R6 | Write API endpoint: POST /api/routes — accepts trip input, returns 3 plans | Richard | Before March 11 | Critical |
| R7 | Write API endpoint: POST /api/predict — calls Lambda ML function | Richard | Before March 12 | Critical |
| R8 | Write API endpoint: POST /auth/login and POST /auth/register — JWT auth | Richard | Before March 12 | Critical |
| R9 | Test all safety features on a physical Android or iOS device | Richard | Before March 13 | High |

## 6.5  All Team Members

| # | Action Item | Owner | Timeline | Priority |
| --- | --- | --- | --- | --- |
| T1 | Create private GitHub repository 'transiq' — invite all 5 members | Jodel | Before March 9 | Critical |
| T2 | Create Notion workspace 'TransIQ' — add Roadmap, Roles, Notes, Pitch pages | Anyone | Before March 9 | High |
| T3 | Create shared Google Drive folder — upload dataset and Colab notebook | Ayanna | Before March 9 | High |
| T4 | Create WhatsApp or Discord group — all 5 members added | Anyone | Before March 9 | High |
| T5 | Set up AWS account — EKS, Lambda, RDS, API Gateway, Snowflake configured | Richard + Jodel | Before March 12 | Critical |
| T6 | Write Terraform scripts for full AWS infrastructure provisioning | Richard | Before March 12 | High |
| T7 | Set up GitHub Actions CI/CD pipeline — push to main triggers deployment | Richard | Before March 12 | High |
| T8 | Every team member pushes pre-built code to GitHub by end of March 13 | All | March 13 | Critical |
| T9 | Prepare and rehearse 5-minute demo script as a full team | All | March 13 | Critical |
| T10 | Pre-load demo data — 5 realistic users with saved routes and trip history | Abby | March 13 | High |
| T11 | Write project README — problem, solution, tech stack, setup instructions | Anyone | March 15 PM | High |

# 7. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Scraper breaks on hackathon day | Medium | High | Keep synthetic dataset as fallback — app still works with pre-loaded data |
| ML model accuracy is poor | Low | High | Validate MAE before hackathon. Retrain on live data. Accept slightly higher MAE if needed. |
| AWS deployment fails | Medium | Critical | Test Terraform scripts before March 13. Have Richard run a full dry-run deploy. |
| Team member falls behind on pre-build | Medium | High | Daily check-ins from March 9. Pair up if someone is blocked. |
| App crashes during live demo | Low | Critical | Pre-load one demo scenario that always works. Practice demo 3 times before presenting. |
| Google Maps API quota exceeded | Low | Medium | Set up billing alerts. Have a static map screenshot as backup for the demo. |

# 8. Success Metrics

Winning Condition A fully deployed, live app with a working Kafka real-time update, ML predictions returning in under 2 seconds, and a compelling 5-minute demo that ends with a live URL judges can open on their own phones.

| Judging Criterion | Weight | Our Target | How We Hit It |
| --- | --- | --- | --- |
| Technical Execution | 30% | 9.5 / 10 | Full stack: Kafka + ML Lambda + Snowflake + CI/CD deployed on AWS EKS |
| Innovation & Creativity | 20% | 8.5 / 10 | Live web scraping + crowdsourced fares + first-ever Jamaica transport app |
| Impact & Business Viability | 20% | 9.5 / 10 | Ministry of Transport pitch angle + tourism secondary market + island wide coverage |
| User Experience & Design | 15% | 8.5 / 10 | Waze-level interactive map, dark UI, real-time traffic alerts, safety features |
| Presentation | 15% | 9 / 10 | Scripted 5-min demo with Kafka live update moment + business pitch close |

| Metric | Target |
| --- | --- |
| Win probability (1st place) | 65–72% |
| Win probability (top 3) | 80–85% |
| ML ETA prediction MAE | Under 8 minutes |
| ML Fare prediction MAE | Under JMD 50 |
| API response time | Under 2 seconds |
| App tested on platforms | iOS and Android both |
| Demo rehearsals completed | Minimum 3 full run-throughs |